# STATUS

Nidan · generated from docs/build-log/STATUS.md on 2026-09-21

# Build status

| Generated | 2026-09-14 — python scripts/build_status.py |
| --- | --- |
| Source | docs/spec/BUILD_PLAN.md (do not edit this file by hand) |
| Tasks complete | 16 of 34 (47%) |
| Effort | 26 d done · 57 d remaining |
| Branch | docs/phase-1-consistency |
| Last commit | 84bcac4 Merge remote-tracking branch 'origin/docs/phase-1-consistency' into docs/phase-1-consistency |

Estimates are engineering effort only. They do not include the clinical content authoring that BUILD_PLAN §11.1 rates the real critical path — see the last section.

## Phases at a glance

| Phase | Tasks | Done | Effort left | Status |
| --- | --- | --- | --- | --- |
| Phase 0 — Foundation | 7 | 7 | 0 d | ✅ complete |
| Phase 1 — Persistence and accounts | 9 | 9 | 0 d | ✅ complete |
| Phase 2 — Admin console P0 | 4 | 0 | 12 d | ⬜ not started |
| Phase 3 — API and web app | 8 | 0 | 28 d | ⬜ not started |
| Phase 4 — Commercial readiness | 6 | 0 | 17 d | ⬜ not started |

## Phase 0 — Foundation

7 of 7 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ✅ | T-001 · Restructure into a nidan/ package | Vraj | 2 d | — | [T-001](T-001-package-restructure.md) |
| ✅ | T-002 · Test harness and fake LLM gateway | Vraj | 2 d | T-001 | [T-002](T-002-test-harness.md) |
| ✅ | T-003 · Lexicon disjointness test ⭐ | Vraj | 0.5 d | T-002 | [T-003](T-003-case-invariants.md) |
| ✅ | T-004 · CI pipeline with the validation gate ⭐ | Vraj | 1 d | T-002 | [T-004](T-004-ci-validation-gate.md) |
| ✅ | T-005 · Docker + docker-compose | Vraj | 1 d | T-001 | [T-005](T-005-docker-compose.md) |
| ✅ | T-006 · Typed configuration | Vraj | 1 d | T-001 | [T-006](T-006-typed-configuration.md) |
| ✅ | T-007 · Structured logging and Sentry | Vraj | 0.5 d | T-006 | [T-007](T-007-telemetry.md) |

## Phase 1 — Persistence and accounts

9 of 9 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ✅ | T-010 · Schema and migrations | Vraj | 3 d | T-005 | [T-010](T-010-schema-and-migrations.md) |
| ✅ | T-011 · Seed content and openapi.yaml skeleton ⭐ | Vraj | 2 d | T-010 | [T-011](T-011-seed-content-and-openapi.md) |
| ✅ | T-012 · Repository layer and tenant scoping | Vraj | 2 d | T-010 | [T-012](T-012-repository-layer-and-tenant-scoping.md) |
| ✅ | T-013 · Event-sourced session state ⭐ | Vraj | 3 d | T-012 | [T-013](T-013-event-sourced-session-state.md) |
| ✅ | T-014 · Supabase Auth integration | Vraj | 2 d | T-012 | [T-014](T-014-supabase-auth-integration.md) |
| ✅ | T-015 · Anonymous trial sessions | Vraj | 1.5 d | T-013,T-014 | [T-015](T-015-anonymous-trial-sessions.md) |
| ✅ | T-016 · Assessment from events ⭐ | Vraj | 2 d | T-013 | [T-016](T-016-assessment-from-events.md) |
| ✅ | T-017 · Free-tier allowance and case selection | Vraj | 1.5 d | T-014 | [T-017](T-017-free-tier-allowance-and-case-selection.md) |
| ✅ | T-018 · Pilot data backfill | Vraj | 1 d | T-016 | [T-018](T-018-pilot-data-backfill.md) |

## Phase 2 — Admin console P0

0 of 4 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ⬜ | T-020 · Admin shell and auth | Yogesh | 1 d | T-014 | — |
| ⬜ | T-021 · Case editor ⭐ | Yogesh | 5 d | T-020,T-011 | — |
| ⬜ | T-022 · Playtest with live instrumentation ⭐ | Yogesh | 4 d | T-021,T-016 | — |
| ⬜ | T-023 · Clinical review workflow ⭐ | Yogesh | 2 d | T-022 | — |

## Phase 3 — API and web app

0 of 8 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ⬜ | T-030 · JSON API ⭐ | Vraj | 6 d | T-016,T-017 | — |
| ⬜ | T-031 · LLM gateway hardening | Vraj | 2 d | T-006 | — |
| ⬜ | T-032 · Next.js scaffold and auth | Yogesh | 4 d | T-011 | — |
| ⬜ | T-033 · Dashboard and onboarding | Yogesh | 3 d | T-032 | — |
| ⬜ | T-034 · Consultation screen ⭐ | Yogesh | 6 d | T-030,T-032 | — |
| ⬜ | T-035 · Real-patient-data guard | Vraj | 1 d | T-034 | — |
| ⬜ | T-036 · Feedback screen ⭐ | Yogesh | 3 d | T-030,T-032 | — |
| ⬜ | T-037 · History and progress | Yogesh | 3 d | T-036 | — |

## Phase 4 — Commercial readiness

0 of 6 complete

|  | Task | Owner | Est | Depends | Build log |
| --- | --- | --- | --- | --- | --- |
| ⬜ | T-040 · Leakage monitor ⭐ | Vraj | 3 d | T-030 | — |
| ⬜ | T-041 · Stripe subscriptions | Vraj | 4 d | T-030 | — |
| ⬜ | T-042 · Pricing and account screens | Yogesh | 3 d | T-041,T-032 | — |
| ⬜ | T-043 · AI usage and cost dashboard | Yogesh | 2 d | T-031,T-020 | — |
| ⬜ | T-044 · Master list and lexicon editors | Yogesh | 3 d | T-020 | — |
| ⬜ | T-045 · Launch readiness | Both | 2 d | all above | — |

⭐ marks a task the plan flags as load-bearing — it protects a property in CLAUDE.md, unblocks another track, or closes a known risk.

A task shows ✅ only when its BUILD_PLAN entry carries a DONE marker. Every completed task has a build log recording what was actually built, where it diverged from the specification, and what debt it left.

Phases 5–7 are not listed. BUILD_PLAN §9 summarises them as prose rather than itemised tasks — measurement upgrade (11 d), mobile (20 d) and Case Factory (22 d) — and they are expanded when the phase begins. The counts above therefore cover the work through launch, which is what there is to track today.

## The thing this table cannot show

Every number above is engineering effort. Ten clinically reviewed cases gate launch and five exist. No task in this plan produces one: writing a case is clinical authoring, not development, and it needs no developer time.

The two clinician reviewers cannot start until T-021 (case editor) and T-023 (review workflow) exist, because until then only a programmer can read a case. That is 12 days of Phase 2 work away, and authoring the drafts can begin before it.

BUILD_PLAN §11.1 rates this the risk to the schedule, and it is the one a task tracker makes easy to forget — because it has no task.